|  |
| --- |
| **Proposal to Reorganise the Catholic Education Provision in Flintshire** |
|  |  |  |
| **Anticipated Timeline** |  |
|  |  |  |
| **DATE** | **SCHOOL TERM** | **KEY MILESTONE** |
| February 2025 | Spring 2025 | Cabinet presented with proposal and approval sought to proceed to Approval to commence with Statutory Proposals |
| March 2025 | Spring 2025 | Consultation document published. Must be published on a school day (42 days with 20 school days) |
| April 2025 | Spring 2025 | Consultation Ends |
| June 2025 | Summer 2025 | Publication of Consultation Report (at least 2 weeks prior to publishing a notice) |
| July 2025 | Summer 2025 | Cabinet review of consultation report and decision on whether or not to proceed to a Notice |
| September 2025 | Autumn 2025 | If agreed Statutory Notice published providing a 28 day period for objections. (Must be published on a school day and with 15 school days in the period) |
| September 2025 | Autumn 2025 | End of objection period |
| December 2025 | Spring/Autumn 2026 | Cabinet Determination and Publication of Objection report. (Must be done within 7 days of the date of determination) |
|  |  |  |
| Note: the anticipated timeline is a guide to the statutory process and is subject to change |